## Sheet1
AppLCC Annual Planning Cycle
Description | Jan-1 | Jan-15 | Feb-1 | Feb-15 | Mar-1 | Mar-15 | Apr-1 | Apr-15 | May-1 | May-15 | Jun-1 | Jun-15 | Jul-1 | Jul-15 | Aug-1 | Aug-15 | Sep-1 | Sep-15 | Oct-1 | Oct-15 | Nov-1 | Nov-15 | Dec-1 | Dec-15
SIAS Report (draft) to Staff |  | 15th
SIAS Report (draft) to KE & AM
SIAS Report Due to Natl LCC (Distributed) |  | 24th
Annual Report (text) Due to Natl LCC (Distributed) |  | 24th
Annual Report (text) finalized - to layout |  | d | 7th
Annual Report Print-version to JB |  |  | 14th
Annual Report to Printers (+ pdf Posted/emailed) |  |  |  | 21st-28th
Annual DVD List Completed
Burn DVDs
Send out DVDs
RFP - 4th Q previous year Reports Due |  | 31st
TOT Comments Due (4th Q previous year) |  |  | 14th
RFP - 1st Q Reports Due | [7 empty] | 30th
TOT Comments Due (1st Q) | [8 empty] | 14th
RFP - 2nd Q Reports Due | [13 empty] | 31st
TOT Comments Due (2nd Q) | [14 empty] | 14th
RFP - 3rd Q Reports Due | [19 empty] | 31st
TOT Comments Due (3rd Q) | [20 empty] | 14th
Winter Newsletter 0-draft (to Team) |  |  |  | 20th
Winter Newsletter 1st Draft (to JB) |  |  |  |  | 1st
Winter Newsletter Due | [5 empty] | 15th
Spring Newsletter 0-draft (to Team) | [9 empty] | 20th
Spring Newsletter 1st-draft (to JB) | [10 empty] | 1st
Spring Newsletter Due (distributed) | [11 empty] | 15th
Summer Newsletter 0-draft (to Team) | [15 empty] | 20th
Summer Newsletter 1st draft (to JB) | [16 empty] | 1st
Summer Newsletter Due | [17 empty] | 15th
Fall Newsletter 0-draft (to Team) | [21 empty] | 20th
Fall Newsletter 1st-draft (to JB) | [22 empty] | 1st
Fall Newsletter Due | [23 empty] | 15th
Science Needs Portfolio (COPs + IPT invited)
Science Needs Portfolio (1st Review Call)
Science Needs Portfolio (2nd Review Call)
Science Needs Portfolio (IPT Review Call)
Science Needs Portfolio (Distributed)
R5- SA Retreat
R4-SA Retreat
Congressional Hill Visits (John)
North American Conference
NEAFWA Conference | [6 empty] | 13th-15th
SEAFWA Conference | [19 empty] | 19th-22nd
National LCC Coordinators Meeting #1 | [12 empty] | Meeting @ NCTC
National LCC Coordinators Meeting #2
National LCC Communications Meeting (No Meeting Scheduled))
NALCC SC Meeting #1 | [7 empty] | 16th-17th
NALCC SC Meeting #2 | [20 empty] | Sometime in Nov.
SALCC SC Meeting - Monthly Call
SALCC SC Meeting #1 | [5 empty] | 25th-27th
SALCC SC Meeting #2
GCPO LCC SC Meeting #1 | [7 empty] | 22nd-24th
GCPO LCC SC Meeting #2
ETGP LCC SC Meeting #1 | [13 empty] | 23-24
ETGP LCC SC Meeting #2
SE CSC - Advisory Call #1 | [6 empty] | 7th-15th
SE CSC - Advisory Call #2
SE CSC - Call for SOI | [10 empty] | 10th
SE CSC - Review of Proposals | [11 empty] | Review | Review
SE SCS - Selection of Proposals | [22 empty] | 1st
NE CSC - Advisory Call #1 | [6 empty] | 7th-15th
NE CSC - Advisory Call #2
NE CSC - Call for SOI | [10 empty] | 10th
NE CSC - Review of Proposals | [11 empty] | Review | Review
NE SCS - Selection of Proposals | [22 empty] | 1st
AMJV Management Board Meeting | [9 empty] | 22nd-23rd
AMJV Technical Meeting | [15 empty] | 19th-20th
CHJV Management Board Meeting | [7 empty] | 29th-1st
CHJV Technical Meeting - Not Scheduled Yet
JV - National Meeting - Not Scheduled Yet
JV - National Communicators' Meeting | [17 empty] | 16th-18th
National FHP Annual Meeting |  |  |  |  | 10th-12th | [13 empty] | Sometime in Oct.
EBTJV Meeting | [16 empty] | 8th- 9th
SARP Meeting (Lindsay) | [8 empty] | 6th (Call) | [9 empty] | Sometime in Oct.
ORB FHP Meeting
Atlantic Coast FHP Meeting